## Defects
Sl No | Submitted By | Submitted Date | Description | Detected Sprint | Assigned To | User Interface | Action Taken | Action Taken Date | Status(Open/Closed) | Remarks
1 | Arepalli Gireesh kumar gowd | 16-2-26 | OCR misreading fields in low-quality document images | Sprint 2 | Arepalli Gireesh kumar gowd | Maintainability | Applied preprocessing (grayscale, thresholding) and improved OCR pipeline | 16-2-26 | Open | Accuracy improved but not fully resolved
2 | Arepalli Gireesh kumar gowd | 2026-03-09 | GNN anomaly score exceeding expected range (0–6), producing values 120–400 | Sprint 6 | Arepalli Gireesh kumar gowd | Logical | Normalized output using scaling and adjusted activation function | 2026-03-09 | Closed | Model outputs now within expected range
3 | Arepalli Gireesh kumar gowd | 2026-03-22 | MongoDB schema validation blocking saves due to strict enum and max value constraints | Sprint 10 | Arepalli Gireesh kumar gowd | Logical | Relaxed schema rules and updated validation logic | 2026-03-22 | Closed | Data insertion working correctly
4 | Arepalli Gireesh kumar gowd | 2026-03-22 | Groq LLM occasionally parsing incorrect fields from documents | Sprint 9 | Arepalli Gireesh kumar gowd | Logical | Added prompt tuning and validation checks for extracted fields | 2026-03-22 | Open | Needs further refinement
5 | Arepalli Gireesh kumar gowd | 22-3-26 | Package version conflicts between TensorFlow, OpenCV, and OpenBharatOCR | Sprint 12 | Arepalli Gireesh kumar gowd | Standards | Resolved by fixing compatible versions, creating requirements.txt and using virtual environment | 2026-04-02 | Closed | Stable environment achieved
6 | Sriram Sannidhi | 25-3-26 | Frontend api.js calling ML service directly (detectDocumentType, extractOCRText) bypassing backend. Architecture violation causing CORS errors and broken auth. | Sprint 14 | Sriram Sannidhi | Logical | Removed all direct ML API functions from frontend api.js. Single entry point verifyDocument() routes all calls through backend /api/kyc/verify. | 2026-03-18 | Closed | Frontend now correctly routes through backend only. Direct ML calls fully removed.
7 | Sriram Sannidhi | 25-3-26 | Backend Node.js server binding to 127.0.0.1 (localhost) only. External HTTP requests from browser and other services cannot reach port 5000 — connection refused from any external IP. | Sprint 14 | Sriram Sannidhi | Logical | Changed app.listen(PORT) to app.listen(PORT, '0.0.0.0') in server.js. This binds the server to all network interfaces, allowing external access. | 2026-03-22 | Closed | curl from local Mac confirmed: 'KYC Compliance Backend is running'. External access working.
8 | Sriram Sannidhi | 25-3-26 | Frontend deployed on AWS S3 returns CORS error when calling backend EC2 API. Browser blocks requests with: Access-Control-Allow-Origin mismatch. Backend CORS config only allowed http://localhost:5173 — does not include the S3 bucket URL. | Sprint 14 | Sriram Sannidhi | Logical | Updated CORS configuration in server.js to include S3 URL in allowed origins array: ['http://localhost:5173', 'http://<bucket>.s3-website-<region>.amazonaws.com']. Restarted backend via pm2 restart backend. | 2026-03-28 | Closed | S3-hosted frontend can now successfully call backend API. Login, upload, and verification all working from public URL.
9 | Sriram Sannidhi | 25-3-26 | PM2 launches ML Flask service using system Python 3.12 which has no ML dependencies installed. ML service shows 'online' in pm2 list but immediately crashes with ModuleNotFoundError: No module named numpy. venv is not activated by PM2 by default. | Sprint 14 | Sriram Sannidhi | Logical | Changed PM2 start command to explicitly use venv Python interpreter: pm2 start app.py --name ml-service --interpreter /home/ubuntu/ml-service/venv/bin/python. This bypasses need to activate venv manually. | 2026-03-28 | Closed | ML service running stably under PM2. Persists across SSH disconnects. pm2 logs ml-service shows all models loaded successfully.
10 | Sriram Sannidhi | 25-3-26 | Invalid document uploaded by user (e.g. wallpaper, random image not a KYC document). System previously had no graceful handling — could crash backend or return malformed response causing unhandled UI state. | Sprint 14 | Sriram Sannidhi | User Interface | ML service returns document_type: 'Non-KYC Document' for unrecognised images. Backend normalizeDocumentType() maps this correctly. Frontend displays 'Non-KYC Document' result state with appropriate messaging rather than crashing. | 2026-03-28 | Closed | Invalid document testing confirmed: system correctly identifies and displays Non-KYC result. No crashes or unhandled states observed.